Australian Service Excellence Standards (ASES) Project Plan

About this Template

The Highwire Groups is sending you this Planning Template as a valued client.

To maintain ASES accreditation, you are required to undertake an External Assessment (‘Assessment’) every three years.

The process for your re-assessment will be similar to your past experience.  This might be a helpful checklist as you prepare. You can easily tailor it to work best for your organisation.

This Project Plan is aligned to the seven main steps developed by the ASES Team at the 
Department for Human Services, SA – the owner of the Standards.   It is intended as a guide only.

# Outline of the ASES Re-Assessment Process

| BEFORE ASSESSMENT | Step 1. Pre-Assessment Information Gathering and Tasks |
| --- | --- |
|  | Step 2. Registration |
|  | Step 3. Self-Assessment and Document Collection |
|  | Step 4. Book and Prepare for Assessment |
| DURING ASSESSMENT | Step 5. On-site Assessment |
| AFTER ASSESSMENT | Step 6. Report and Quality Action Plan |
|  | Step 7. Accreditation Decision |

BEFORE ASSESSMENT

Step 1. Pre-Assessment Information Gathering and Tasks

| MAIN TASK | ACTIONS | RESPONSIBLITY | BY WHEN | COMPLETED | NOTES |
| --- | --- | --- | --- | --- | --- |
| Select your Assessor | There is a list of eligible External Assessors on the SA Human Services’ ASES webpage Highwire is an approved External Assessor (see our video Why Choose Highwire to find out more about us and how we work) |  |  |  | Highwire would welcome the opportunity to conduct your ASES assessment again. We will contact you 1 year prior to your re-assessment date |
|  | Highwire can provide a quote for your Assessment based on the details of your organisation – see the Assessment costs on the ASES website/External Assessment Costs |  |  |  | Highwire will need to know the number of sites and number of staff within the assessment to provide a quote Our ASES Fees are on our website |
|  | Discuss with CEO/management as required to make a preference decision |  |  |  |  |
|  | Sign and return the Highwire Service Agreement This will activate an invoice for 50% of the total fee |  |  |  |  |

Step 2. Registration

| MAIN TASK | ACTIONS | RESPONSIBLITY | BY WHEN | COMPLETED | NOTES |
| --- | --- | --- | --- | --- | --- |
| Register with ASES Team | Register for an Assessment by completing the online ASES Activity Form on the SA Human Services’ ASES website |  |  |  | When the registration form is received by the ASES Team they will enter your organisation into their database – this does not commit you to an Assessment, but will give you the ability to access ASES workbooks and other materials and information |
|  | Keep a copy of registration information to show your assessor |  |  |  |  |
|  | Receive details from the SA Human Services’ ASES Team to access resources, workbooks and evidence guides through the Partnership Portal |  |  |  |  |
| Explore eligibility for funding | After Registration is confirmed by the ASES Team, check with them if you are eligible for funding – serviceexcellence@sa.gov.au, ph. 08 8413 9036 (SA only) In NSW contact your Industry partner or DCJ contract manager to see if you may be eligible for funding. Or check the Homelessness NSW ASES Support Page for eligibility for a grant to help with assessment costs. |  |  |  |  |
| Self-funding | If you are not eligible for funding you will need to arrange to self-fund your Assessment Inform CEO or management as required for decision |  |  |  |  |

Step 3. Self-Assessment and Document Collection

At this stage you complete the Workbook or Portal  that asks you to document your systems, practice and behaviours for each Standard. You will also gather evidence to support the information in your Workbook or Portal. During this process you will begin to understand how 'ready' you are to gain Accreditation and how much work you need to do to successfully undertake your Assessment.

| MAIN TASK | ACTIONS | RESPONSIBLITY | BY WHEN | COMPLETED | NOTES |
| --- | --- | --- | --- | --- | --- |
| Establish support for the process | Identify an Assessment contact, project lead or person responsible for driving the process within your organisation |  |  |  |  |
|  | Share information with Board, management and staff |  |  |  |  |
|  | Consider ways to get buy-in at all levels of your organisation |  |  |  |  |
| Get additional assistance to prepare | - Highwire has a team of consultants who can assist you to with Gap analysis Service development review Systems development Policy advice Coaching and support Training and development |  |  |  | You can arrange for additional assistance at different stages of your preparation as you think it is required |
| Undertake your Self-Assessment | - There are 2 main parts to the Self-Assessment process: Completing the Workbook or BNG Portal quizzes Collecting and collating documentation and evidence of your practice |  |  |  | You can access the ASES Evidence Guide from the SA Human Services’ ASES Team. It provides examples of evidence for each standard |
|  | Establish a process to collect and collate evidence |  |  |  | Develop a process so you can keep track of evidence you will provide to the assessment process. (Folders for hard copy documents aligned to each Standard works well, and these can then be saved and sent to or presented to your Assessor when complete) |
|  | Allocate Workbook or Portal completion tasks to your team |  |  |  |  |
|  | Set up regular meetings to track progress and coordinate collection and recording of documents |  |  |  |  |
|  | Report progress to CEO/management as required |  |  |  |  |

Step 4. Book and Prepare for Assessment

Once you have decided to undertake an Assessment formal notification of dates is made to DHS.

If your funding is dependent on Accreditation, make sure you complete your Assessment in time to fulfill your contract requirements.

| MAIN TASK | ACTIONS | RESPONSIBLITY | BY WHEN | COMPLETED | NOTES |
| --- | --- | --- | --- | --- | --- |
| Engage with your Assessor | Arrange a pre-assessment meeting with your Assessor to go over the process and talk about how to ensure a successful Assessment |  |  |  |  |
| Book your Assessment | Decide on dates for your Assessment with your Assessor |  |  |  | You may need to talk with your management, CEO or Board about this decision |
|  | Your Assessor will inform the ASES Team of the date of your Assessment |  |  |  |  |
| Develop the Assessment Timetable | Work with your Assessor to decide on the timetable for the on-site Assessment |  |  |  | You have an opportunity prior to your Assessment to allocate times for all the Assessment activities – interviews, document review and site inspections This will be done during the pre-assessment meeting |
|  | Share information with the people who will be involved |  |  |  |  |
|  | Consider workshops with staff and Board for understanding about the process and the best way to tell the Assessor about your achievements |  |  |  |  |
| Consider Interviews | Work out groups and group personnel to be interviewed |  |  |  |  |
| Confirm Timetable | Once decisions have been made about the timetable, complete the Assessment Timetable document including group and individual Interviews, and times for documentation review |  |  |  | Highwire can send an Assessment Timetable template for you to complete |
|  | Send draft Timetable to your Assessor |  |  |  |  |
|  | Agree the final Timetable with your Assessor |  |  |  | This needs to be completed 3 weeks prior to the on-site Assessment |
|  | Notify personnel that they will be part of the Interview process |  |  |  |  |
| Make sure Workbook or Portal is completed | Check that all Standards in the Workbook or portal have been adequately addressed |  |  |  |  |
| Make sure documentation is ready | Check that all documents and evidence is ready and available |  |  |  | At least 2 weeks prior to the assessment visit |
| Send key information to Assessor | Send completed Workbook and key organisational documents to your Assessor or provide access to the portal. |  |  |  | 3 weeks prior to your Assessment Your Assessor will let you know what they need to see in advance of the Assessment |
| Pre assessment meeting | Meet with your assessor online to talk through the detail of the visit Make sure your Assessor will have easy access to all documents and other material evidence during the on-site Assessment |  |  |  |  |
|  | Ensure all people involved in the process are available and prepared for their contribution |  |  |  |  |
| House Keeping | Book a confidential work space for Assessor for the duration of the Assessment |  |  |  |  |
|  | Arrange for Internet/Wi-Fi to be accessible in the work space |  |  |  |  |
|  | Consider and arrange for catering for the duration of the Assessment |  |  |  |  |

DURING ASSESSMENT

Step 5. On-site Assessment

The on-site Assessment usually takes two or three days, depending on the size of your organisation. There are three main parts to the Assessment process 
on-site – interviews, document review and site inspections. A feedback session is held at the end of the Assessment visit to let you know how things went.

| MAIN TASK | ACTIONS | RESPONSIBLITY | BY WHEN | COMPLETED | NOTES |
| --- | --- | --- | --- | --- | --- |
| Check readiness |  |  |  |  |  |
| Housekeeping | Check all administrative requirements are in place for your Assessor: - confidential work space - WIFI access - Document and evidence access - Catering |  |  |  |  |
| Timetable | Ensure all requirements for interviews are ready: - Participants - Room & furniture - Whiteboard, audio visual, stationary etc - Refreshments and water |  |  |  |  |
|  | Allocate responsibility for day-to-day management of the Assessment |  |  |  | It is your organisation's responsibility to manage the on-site process each day of the Assessment |
| Facilitate the process |  |  |  |  |  |
| Site Inspections | Ensure someone is available to escort your Assessor around the buildings for WHS site inspections |  |  |  |  |
| Manage the Timetable | Liaise with Assessor to facilitate: - Interviews - Site inspections - Document review |  |  |  |  |
| Manage catering | Morning tea, afternoon tea and lunch for Assessor |  |  |  |  |
|  | Drinking water for Assessor and participants |  |  |  |  |
| Adapt to changes | Facilitate any change in the Timetable |  |  |  |  |
|  | Provide additional evidence as required by Assessor |  |  |  |  |
| Check progress | Catch up with Assessor and your team to check how things are going |  |  |  |  |

AFTER ASSESSEMENT

Step 6. Report and Quality Action Plan

After your Assessment you will receive a detailed Draft Report to check for accuracy, then your Assessor will send your final External Assessment Report to you and the ASES Team. Your Report is likely to include some recommendations and some may need to be addressed before Accreditation can be granted.

There are two types of Recommendations for improvement that your Assessor can make – Continuous Quality Improvement (to assist you to continue your quality journey within your own framework) and Essential Recommendation (requiring you to address gaps and report to the ASES Team before Accreditation can be granted).

You will complete a Quality Action Plan (QAP) to guide your improvements.

| MAIN TASK | ACTIONS | RESPONSIBLITY | BY WHEN | COMPLETED | NOTES |
| --- | --- | --- | --- | --- | --- |
| Receive Draft Report | Receive your Draft Report from your Assessor |  |  |  | Within 3 weeks of the last date of the Assessment |
|  | Check draft report for accuracy of fact – discuss any concerns with your Assessor |  |  |  | Within 3 weeks When this is mutually agreed to be correct; it becomes the final External Assessment Report |
| Submission of Report to ASES Team | Highwire Group forwards your final External Assessment Report to both you and the ASES Team |  |  |  | Between 3-6 weeks from the last date of the Assessment |
| Develop Quality Action Plan | Assessor advises ASES Team if a Quality Action Plan (QAP) is required |  |  |  | If your final External Assessment Report includes any Essential Recommendations, you will need to complete a Quality Action Plan (QAP) |
|  | Receive a Quality Action Plan template with the agreed actions/evidence needed (from Assessor) |  |  |  | Return to the Assessor within 2 weeks |
|  | Send your Assessor and ASES Team a copy of the updated QAP with: - agreed actions - evidence - timelines - responsibilities |  |  |  | QAP to be finalised within 6 months from the last date of the Assessment |
| Address recommendations |  |  |  |  |  |
| Implement Quality Action Plan (QAP) | Develop strategies to address gaps |  |  |  | It is essential to develop and document strategies to address your Essential Recommendations – you are required to report on these to the ASES Team to gain Accreditation |
|  | Document strategies in your QAP |  |  |  | It can be helpful to also document strategies for Continuous Quality Improvements (CQI Recommendations) in your QAP so that you have a complete organisational action plan for your quality journey |
| Provide evidence for Essential Recommendations |  |  |  |  |  |
| Send up-dated QAP | Send your updated QAP showing what you have implemented to Service Excellence Team |  |  |  | You will have 6 months after the completion of your Assessment to implement and provide evidence of your quality improvement actions that address any Essential Recommendations |
| Send evidence and QAP | Send your updated QAP along with evidence of the implementation to Highwire |  |  |  | The documentary evidence you provide can vary depending on the requirements, but it could be in the form of: organisational documents communications with staff/clients/stakeholders promotional materials or photographs meeting agendas and notes emails screen dumps website |

Step 7. Accreditation Decision

If Accreditation is granted by the ASES Team, you will receive a Certificate for each accreditation level you achieve (Certificate Level, Award Level).

| MAIN TASK | ACTIONS | RESPONSIBLITY | BY WHEN | COMPLETED | NOTES |
| --- | --- | --- | --- | --- | --- |
| Assessment of evidence of improvements | Highwire will assess your evidence to enable Accreditation |  |  |  |  |
|  | If further evidence is required your Assessor will contact you and discuss |  |  |  |  |
| Reporting to ASES Team | Highwire will communicate with both the ASES Team and you about your Assessment achievement |  |  |  |  |
|  | Highwire Group will inform the ASES Team that the Quality Action Plan is complete and make a recommendation to the ASES Team for Accreditation |  |  |  |  |
| Issuing of Certificate/s | If Accreditation is granted, the ASES Team will contact you and send you your Certificate/s |  |  |  | Usually within 4 weeks of receiving the finalised report from Highwire |
| Display Accreditation status | The ASES Team will also forward to you information about how you are able to both display your Accreditation Certificate and use the ASES Accreditation logo in your promotional materials |  |  |  |  |
| Set date for next External Assessment | The next Assessment date will be 3 years after the last date of each Assessment |  |  |  | Highwire will contact you 1 year out |